**Performance in Delivering Q2 19/20**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **REC Reference** | **IRAS Number** | **Name of Trial** | **Target number of Patients Agreed?** | **Minimum number of patients agreed (Enter same in both if only one number)** | **Maximum number of patients agreed (Enter same in both if only one number)** | **Target Date to recruit patients agreed?** | **Date agreed to recruit target number of patients?** | **Total number of patients recruited at the agreed target date** | **Date that the trial closed to recruitment** | **Total number of study participants recruited** | **Reason for closure of trial** | **Comments** |
| 17/LO/0030 | 200764 | Feasibility randomised controlled trial of individual Cognitive Stimulation Therapy (iCST) for dementia in people with intellectual disability | Number agreed | 6 | 6 | Date Agreed | 31/01/2019 | 4 | 21/12/2018 | 4 | Withdrawn by Sponsor | Recruitment target met nationally, study closed early by sponsor with final dyad not recruited within reported period. |
| 17/NW/0688 | 225304 | Connecting People Implementation Study | Number agreed | 42 | 42 | Date Agreed | 31/01/2019 | 50 | 10/10/2018 | 50 | Recruitment finished | Recruitment target met |
| 14/NW/1423 | 155550 | European Long-acting Antipsychotics in Schizophrenia Trial: EULAST | Number agreed | 2 | 2 | Date Agreed | 31/12/2018 | 2 | 31/12/2018 | 2 | Recruitment Finished |  |