**Performance in Delivering Q3 19/20**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **REC Reference**  | **IRAS Number** | **Name of Trial** | **Target number of Patients Agreed?** | **Minimum number of patients agreed (Enter same in both if only one number)** | **Maximum number of patients agreed (Enter same in both if only one number)** | **Target Date to recruit patients agreed?** | **Date agreed to recruit target number of patients?** | **Total number of patients recruited at the agreed target date** | **Date that the trial closed to recruitment** | **Total number of study participants recruited** | **Reason for closure of trial** | **Comments** |
| 18/YH/0433 | 255752 | Managing Unusual Sensory Experiences in people with an At Risk Mental States for Psychosis (MUSE-ARMS) | Number agreed | 14 | 14 | Date Agreed | 28/09/2019 | 17 | 01/09/2019 | 17 | Recruitment Finished |  |
| 17/LO/0987 | 215947 | A feasibility study and pilot trial of a modified video-feedback intervention for children and foster carers to improve mental health outcomes of children with reactive attachment problems | Number agreed | 4 | 4 | Date Agreed | 30/09/2019 | 4 | 30/09/2019 | 4 | Recruitment Finished |  |
| 18/YH/0380 | 249030 | Multi-Morbidity in Older Adults with Depression (MODS): Work Stream 1 (WS1) | Number agreed | 10 | 10 | Date Agreed | 31/08/2019 | 50 | 31/08/2019 | 50 | Recruitment Finished |  |
| 18/WM/0076 | 236872 | Management of sexual dysfunction associated with antipsychotic drugs | Number agreed | 18 | 18 | Date Agreed | 31/10/2020 | 13 | 31/07/2019 | 13 | Withdrawn by sponsor | Study closed early due to recruitment target not met nationally and therefore funding withdrawn |