**Performance in Initiating research Q3 19/20**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **REC Reference** | **IRAS Number** | **Name of Trial** | **Date of First Patient Recruited** | **Date Site Invited** | **Date Site Selected** | **HRA Approval Date** | **Date Site Confirmed By Sponsor** | **Date Site Confirmed** | **Date Site Ready To Start** | **Reasons for delay** | **Comments** | **Reasons for delay correspond to:** |
| 18/YH/0499 | 258585 | Smoking Cessation Intervention for Severe Mental Ill Health Trial (SCIMITAR): a definitive randomised evaluation of a bespoke smoking cessation service. Extended follow up. | 11/02/2019 | 13/09/2018 | 29/01/2019 | 25/01/2019 |  | 31/01/2019 | 06/02/2019 |  |  |  |
| 19/LO/0088 | 257667 | A randomised controlled trial of a structured intervention for expanding social networks in psychosis | 11/03/2019 | 12/12/2018 | 18/02/2019 | 24/01/2019 |  | 11/03/2019 | 11/03/2019 |  |  |  |
| 18/SS/0118 | 241606 | Women Offenders Repeat Self-Harm Intervention Pragmatic Trial (WORSHIP III) | No | 07/11/2018 | 11/03/2019 | 01/03/2019 |  | 16/04/2019 | 16/04/2019 | Sponsor Delays | Sponsor delay in giving green light as amendment needed to ethics committee. | Sponsor |
| 18/EM/0262 | 245510 | A randomised controlled trial evaluating the efficacy of Dialectical Behavioural Therapy Skills for Employment (DBT-SE) compared with a referral to a mental health employment specialist for people with difficulties consistent with a personality disorder (PD). | No | 19/01/2017 | 02/07/2019 | 21/11/2018 |  | 01/08/2019 | 05/08/2019 | Other | Participants consented to trial however awaiting randomisation to be recruited. | Neither |
| 19/YH/0111 | 249633 | Priming Attachment Security within an IAPT setting: A Feasibility and Pilot Study | No | 10/02/2018 | 13/07/2019 | 10/06/2019 |  | 26/07/2019 | 30/07/2019 | No Patients seen | No recruitment as no participants identified by clinicians supporting the study. | Neither |